## Sheet1
Work Estimation Details |  | Optimistic | Most Likely | Pessimistic | Confidence | 75% | 85% | 95% | 99.5% | Supporting Document Links: (Enter Links to Requirements, Specifications, or other supporting documents in this column)
SDLC Phases | Activity/Task (Requirement number) | Effort Hrs | Effort Hrs | Effort Hrs | Factor | Confidence | Confidence | Confidence | Confidence
Construction
| Coding based on priority |  |  |  | 0 | 0 | 0 | 0 | 0
| REQ 1 | 2 | 3 | 5 | 0.5 | 3.1667 | 3.6667 | 4.1667 | 4.6667
| REQ 2 | 2 | 3 | 5 | 0.5 | 3.1667 | 3.6667 | 4.1667 | 4.6667
| REQ 3 | 2 | 3 | 5 | 0.5 | 3.1667 | 3.6667 | 4.1667 | 4.6667
| REQ 4 | 3 | 8 | 10 | 1.1667 | 7.5 | 8.6667 | 9.8333 | 11
| REQ 5 | 0.5 | 0.75 | 2 | 0.25 | 0.91667 | 1.1667 | 1.4167 | 1.6667
| REQ 6 | 3 | 4 | 6 | 0.5 | 4.1667 | 4.6667 | 5.1667 | 5.6667
| REQ 7 | 2 | 3 | 5 | 0.5 | 3.1667 | 3.6667 | 4.1667 | 4.6667
| REQ 8 | 5 | 8 | 10 | 0.83333 | 7.8333 | 8.6667 | 9.5 | 10.3333
| REQ 9 | 5 | 8 | 10 | 0.83333 | 7.8333 | 8.6667 | 9.5 | 10.3333
| REQ 10 | 10 | 15 | 22 | 2 | 15.3333 | 17.3333 | 19.3333 | 21.3333
| REQ 11 | 2 | 3 | 5 | 0.5 | 3.1667 | 3.6667 | 4.1667 | 4.6667
| REQ 12 | 10 | 17 | 25 | 2.5 | 17.1667 | 19.6667 | 22.1667 | 24.6667
[5 empty] | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0
Work Estimate Totals |  | 46.5 | 75.75 | 110 |  | 76.5833 | 87.1667 | 97.75 | 108.3333